## 1_Project Overview
CAPSTONE PROJECT - PROJECT OVERVIEW
Pengelolaan Proyek Sistem Informasi ¦ Kelompok 1
INFORMASI PROJECT |  |  |  | TUJUAN PROJECT | RUANG LINGKUP (SCOPE)
Nama Project |  | Isi nama project |  | 1. Menyelesaikan project sesuai scope dan kebutuhan yang disepakati. | ✓ IN SCOPE • Fitur utama sistem • Database • UI/UX • Testing • Dokumentasi & presentasi
Mata Kuliah |  | Pengelolaan Proyek Sistem Informasi |  | 2. Membagi pekerjaan secara jelas berdasarkan role dan kemampuan anggota.
Dosen Pengampu |  | Lulu Chaerani Munggaran |  | 3. Menjaga progress agar seluruh milestone tercapai sebelum final deadline.
Jumlah Anggota |  | 4/5 orang
Tipe Project |  | Website / Web App / Sistem Informasi
Periode Pengerjaan |  | M1 |  |  | ✕ OUT OF SCOPE • Fitur tambahan di luar kebutuhan utama • Pengembangan di luar batas waktu capstone
Final Deadline |  | M12
PEMBAGIAN PERAN
No. | Nama Anggota | Role Utama | Tanggung Jawab | Backup / Support
1 | Anggia Rahmani Syahdianto | Project Manager (PM) | Planning, timeline, koordinasi, monitoring, integrasi, final presentation | Support seluruh anggota
2 | Sabrina Lulu Yunisa | System Analyst | Requirement, Use Case, Activity Diagram, DFD/UML | PM
3 | Desmawita Hanifah Fitria | UI/UX Designer | User flow, wireframe, UI design, prototype | System Analyst
4 | Maulana Nur Anfajm & Hanif Fityatal Haq | Developer | Frontend/backend, database, integrasi sistem | UI/UX + QA
5 | ALL | QA & Documentation | Test case, testing, bug report, dokumentasi | Developer + PM
Catatan: Sheet ini adalah halaman overview. Detail pekerjaan, PIC, dependency, deadline, dan progress dikelola di sheet berikutnya. |  |  |  |  | CATATAN PM
[5 empty] | Setiap task memiliki PIC dan deadline. | FALSE
[5 empty] | Progress di-update minimal 2× seminggu. | FALSE
[5 empty] | Gunakan internal deadline sebelum deadline dosen. | FALSE
[5 empty] | Task selesai → review → revisi bila perlu → final. | FALSE
[5 empty] | Semua file penting disimpan di satu Google Drive. | FALSE

## 2_WBS & Task
WBS & TASK DETAIL
No. | Tahap | Task | Subtask / Detail | PIC | Output | Dependency | Deadline | Status
1 | Initiation | Brainstorming ide | Identifikasi masalah & ide project | All | Project idea | - |  | Not Started
2 | Initiation | Tentukan scope | Tentukan in-scope & out-of-scope | PM + All | Scope | Brainstorming |  | Not Started
3 | Planning | Project plan | Timeline, role, communication plan | PM | Project plan | Scope |  | Not Started
4 | Requirement | Analisis kebutuhan | Functional & non-functional requirement | System Analyst | Requirement doc | Project plan |  | Not Started
5 | Analysis | System design | Use Case, Activity, DFD/UML, ERD | System Analyst | Design doc | Requirement |  | Not Started
6 | UI/UX | Prototype | Wireframe, UI, user flow, Figma | UI/UX | Prototype | Requirement |  | Not Started
7 | Development | Development | Frontend, backend, database | Developer | MVP/System | Design + Prototype |  | Not Started
8 | Testing | Testing | Test case, bug fixing, retest | QA | Testing report | MVP |  | Not Started
9 | Documentation | Laporan & PPT | Dokumentasi, screenshot, presentasi | QA + All | Final docs | Testing |  | Not Started
10 | Finalization | Rehearsal & submission | Final check & presentasi | All + PM | Final project | All previous |  | Not Started

## 3_Timeline & Gantt
TIMELINE & GANTT CHART
Task | PIC | Start | Deadline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Project Initiation | PM
Planning | PM
Requirement | System Analyst
Analysis & Design | System Analyst
UI/UX | UI/UX Designer
Development | Developer
Testing | QA
Documentation | QA + All
Finalization | All
Legenda | Planned / Active

## 4_Progress Tracker
PROGRESS TRACKER
Task | PIC | Status | Progress % | Deadline | Kendala / Catatan
Brainstorming ide | All | Not Started | 0%
Requirement | System Analyst | Not Started | 0%
UI/UX | UI/UX Designer | Not Started | 0%
Development | Developer | Not Started | 0%
Testing | QA | Not Started | 0%
Dokumentasi | QA + All | Not Started | 0%

## 5_Risk & Issue Log
RISK & ISSUE LOG
No.
1
2
3
4
5
6
7
8
9
10